## Sheet1
Work Breakdown Structure
No. | Type of Task | Description of Task | Output Deliverables | Responsible Person(s) | Deadline
| Project Time |  |  |  | May 17th 2022
1 | Understanding Game Details (From PC Version)
1.1 | Revieing | Team meets to discuss possible business needs. | planning, gathering, and having a single goal in mind | Whole Team | November 17th 2020
1.2 | Data Understanding | It facilitates the discovery of significant connections, patterns, trends, and user behaviour models from existed version of game. | track game-related occurrences with the intention of gathering information for statistical analysis. | Jing Wu (Senior Manager, Analytics Engineering) | November 23th 2020
1.3 | Linked (Open) Data | The linking of disparate sources and formats allows for the induction of new knowledge from existing facts. | connect many existing data sources to create new understanding | Jing Wu (Senior Manager, Analytics Engineering) | December 20th 2020
1.4 | Porting Procedures | act of altering a video game so that a version fit for one platform becomes suitable for another | understand the whole life cycle of porting the game | Sibyl Jin (Production Coordinator) | January 15th 2021
2 | Game Redesigning |  |  | Jordan Patz (Design Director)
2.1 | Adapting the Source Code | Use multifunctional game engines, which provide many useful tools and include platform porting features. | It instructs the machine on how to execute the game in order to play it. |  | January 20th 2021
2.2 | Visual Assets and Optimization | Adding optimized vast maps, powerful characters ,engaging gameplay and the visual element like environment, weapons, fire, smoke, water is what can attract the initial attention to the game. | The game will function properly with fewer resources or with less memory after optimzation of visuals. | Geoff Harrison Jason Shifter Nathan Karklins (Senior Game Designers) | March 20th 2021
2.3 | Using Suitable Middleware | a procedure that is built into a gaming engine to manage a specific specialised component of it, like networking, physics, or graphics. | With a solid understanding of physics, the integration of source code and images will work effectively. |  | April 17th 2021
2.4 | Modernize game controls for mobile | Adapt the controls for the new device while retaining game characteristics through gameplay and design. | Virtual adaptations of the joystick and directional pad will miraculously produce the physical feedback that is missing from a phone or tablet. |  | May 20th 2021
2.5 | Optimizing CPU/GPU Performance | fine-tune the game so that resource usage is optimal - The game runs smoothly on mobile, and the visual quality is adequate. | After graphic optimization, the game will still operate smoothly on less memory or processing power, allowing us to go beyond keeping the graphics high without sacrificing performance. |  | June 10th 2021
2.6 | User Interface and Control Scheme | a mobile platform, given how specialised touchscreen controls are. It ought to have an intuitive user interface, all the required features, and not interfere with gaming. | The UI's clear design and feel will make it just as memorable as the game itself. | Adam Taubenheim (UI/UX Designer) | July 28th 2021
3 | Game Testing |  |  | Anthony Zoghob (QA Development Manager)
3.1 | Alpha Testing | When the game is still in the development phase, parallel testing is performed to ensure that the game is developed without any glitches and runs smoothly without crashing. | find game glitches/bugs, record and fix them to stop from interfering with the gaming experience. |  | November 20th 2021
3.2 | Closed Beta | an internal testing procedure that is not open to the public Beta testing usually refers to the final stages of testing before releasing a product to the public. |  |  | January 15th 2022
3.3 | Open Beta | when the beta version becomes available to anyone who is interested Players test the game for a set period of time and provide early feedback to the development team. |  |  | March 20th 2022
4 | Deployement
4.1 | Relasing the game | rollout of the product written as release notes and support documents on the publishing platform. | publish and distribute. | Alexander Klein (Build and Release Engineer) | May 17th 2022
Created By
Smit Rana [792056]
Ruchit Patel [789968]
Sachin Chaudhary [792544]