## Project Budget
Cost and Budget
Created By :
| Project Budget | Project Info | [6 empty] | Budget Summary |  |  | Ruchit Patel [789968]
| 1950000 |  | Project Lead: | Smit, Niren, Harsh, Sachin, Ruchit |  |  |  | [42] | Budget | Actual | Under(Over) | Sachin Chaudhary [792544]
|  |  | Start Date: | 2020-11-21 |  |  |  |  | 1950000 | 1948010 | 1990
|  | Labor |  | Materials |  | Fixed Costs
| Tasks | Hrs | Rate | Units | $/Unit | Material | Travel | Other | Budget | Actual | Under(Over)
| Project Upfront Cost | [7 empty] | 518900 | 517150 | 1750
| Unreal Game Engine |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Dedicated Game Servers Upfront Cost |  |  | 10 | 9000 |  |  |  | 90000 | 90000 | 0
| Server Installation | 72 | 75 | [5 empty] | 5400 | 5400 | 0
| Server Maintenance | 54 | 50 | [5 empty] | 3500 | 2700 | -800
| Amazon DynamoDB Database Upfront Cost | [6 empty] | 35000 | 35000 | 35000 | 0
| Database Installation and Maintenance | 54 | 75 | [5 empty] | 5000 | 4050 | 950
| Project Insurance | [6 empty] | 50000 | 50000 | 50000 | 0
| Software licence cost for development | [6 empty] | 80000 | 80000 | 80000 | 0
| Office Infrastructure and Workstation cost | [6 empty] | 250000 | 250000 | 250000 | 0
| Project Development | [7 empty] | 1423000 | 1395360 | 27640
| Project Manager | 3840 | 60 | [5 empty] | 225000 | 230400 | -5400
| Programmer | 3840 | 80 | [5 empty] | 310000 | 307200 | 2800
| Game Visual Designer Development Cost | 3840 | 50 | [5 empty] | 200000 | 192000 | 8000
| Game Animator Development Cost | 3840 | 50 | [5 empty] | 200000 | 192000 | 8000
| Video Editor | 720 | 258 | [5 empty] | 190000 | 185760 | 4240
| IT Infrastructure Admin | 3840 | 30 | [5 empty] | 118000 | 115200 | 2800
| Tester | 3840 | 45 | [5 empty] | 180000 | 172800 | 7200
| Project Release | [7 empty] | 35500 | 35500 | 0
| Alpha and Beta Testing | [6 empty] | 10000 | 10000 | 10000 | 0
| Google Play Store/ Apple Store Release | [6 empty] | 25500 | 25500 | 25500 | 0